| ##### WORKPACKAGES | #### Month | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1: Project set up |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2: Specifying the course |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3: Sample unit |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 4: Assembling/writing the course |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 5: Copyright/licensing and multimedia |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 6: Finalising the course content |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 7: Development |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 8: Review and publication |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 9: Delivery |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 10: Evaluation |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 11: Documentation and report writing |  |  |  |  |  |  |  |  |  |  |  |  |  |

Project start date: 01-02-2008

Project completion date: 31-01-2009

Duration:12 months

| ## Workpackage and activity | ## Earliest ## start ## date | ## Latest completion date | Outputs (clearly indicate deliverables & reports in bold) | Milestone | Responsibility |
| --- | --- | --- | --- | --- | --- |
| ## YEAR 1 |  |  |  |  |  |
| ##### WORKPACKAGE 1: Project set up Objective: Set up the project | 01/02/08 | 31/03/08 |  |  |  |
| - Write project plan. | 01/02/08 | 12/03/08 | Project plan | 1 | MM |
| - Create project website and blog | 01/02/08 | 20/02/08 | Project website and Project Blog | 2 | DB |
| - Contract subject matter expert. | 01/02/08 | 31/03/08 |  |  | NW |
| ##### Meet support Project | 20/02/08 | 31/03/08 |  |  | MM, TB |
| ##### Agree peer review partner and process | 20/02/08 | TBC |  |  | MM |
| ##### WORKPACKAGE 2: Specifying the course Objective: Course specified | 28/02/08 | #### 10/04/08 |  |  |  |
| - SME specifies course using TALL standard online course specification process. | 28/02/08 | 13/03/08 |  |  | SB |
| - Specify induction | 28/02/08 | 10/04/08 |  |  | MM |
| - Review course specification | 14/03/08 | 20/03/08 |  |  | MM, DG |
| - Rework as required prior to sign-off by AD and LT | 25/03/08 | 10/04/08 | Course Specification | 3 | SB |
| ##### WORKPACKAGE 3: Sample unit Objective: Sample unit built | 11/04/08 | 28/04/08 |  |  |  |
| - SME assembles learning materials for sample unit, adapts as required, and writes any additional materials | 11/04/08 | 17/04/08 |  |  | SB |
| - Review Sample unit | 17/04/08 | 21/04/08 |  |  | MM, DG |
| - Senior Developer investigates technical issues. | 17/04/08 | 21/04/08 |  |  | DB |
| - LT, SME discuss guidance requirements for rest of course | 17/04/08 | 21/04/08 |  |  | SB, MM |
| - SME reworks content as required prior to sign-off by Academic Director and Learning Technologist. | 21/04/08 | 24/04/08 |  |  | SB |
| - Web developer builds sample unit | 25/04/08 | 28/04/08 | Sample unit | 4 | IG |
| ##### WORKPACKAGE 4: Assembling/writing the course Objective: Course written | #### 11/04/08 | #### 03/10/08 |  |  |  |
| - Assemble learning materials for rest of course, write any additional materials and create tutor notes | 25/04/08 | 09/06/08 |  |  | SB |
| - Assemble learning materials for induction, write any additional materials | 11/04/08 | 03/10/08 |  |  | MM |
| - Content submitted for external academic review. | 10/06/08 | 23/06/08 |  |  | GB |
| - Materials reviewed by LT and AD | 10/06/08 | 23/06/08 |  |  | MM, DG |
| - Materials reworked as required prior to sign-off by Academic Director and Learning Technologist. | 23/06/08 | 28/07/08 | Finalised draft of content signed off | 5 | SB |
| ##### WORKPACKAGE 5: Copyright/licensing and multimedia Objective: copyright cleared and multimedia built | #### 08/03/08 | #### 02/12/08 |  |  |  |
| - Liaise with JISC project support regarding initial communications | #### 08/03/08 | #### 20/03/08 |  |  | TB |
| - SME submits list of external material requiring copyright clearance | #### 25/04/08 | #### 09/06/08 |  |  | SB |
| - 2Feedback comments to SME regarding initial list of external material requiring copyright clearance | #### 10/06/08 | #### 21/07/08 |  |  | TB |
| - SME provides further information and/or amended list | #### 23/06/08 | #### 28/07/08 |  |  | SB |
| - Work with JISC support project to manage copyright clearance and licensing issues | 13/03/08 | 02/12/08 |  |  | TB |
| - Investigate technical repurposing challenges. | 13/03/08 | 02/12/08 |  |  | DB |
| - Adapt and develop any interactive and rich media course elements. | 13/03/08 | 02/12/08 | All copyright cleared and multimedia developed/adapted | 6 | IG |
| ##### WORKPACKAGE 6: Finalising the course Objective: course prepared for build | 06/10/08 | 14/11/08 |  |  |  |
| - Final editorial QA | 06/10/08 | 17/10/08 |  |  | GB |
| - Assemble existing and new content | 06/10/08 | 17/10/08 |  |  | GB |
| - Send for copyedit | 20/10/08 | 24/10/08 |  |  | GB |
| - Prepare materials for build | 10/11/08 | 14/11/08 |  |  | GB |
| - Create course delivery schedule | 10/11/08 | 14/11/08 | Course ready for build | 7 | GB |
| WORKPACKAGE 7: Development Objective: Course built | 10/11/08 | 22/12/08 |  |  |  |
| - Create course in Moodle | 10/11/08 | 10/11/08 |  |  | MT |
| - Incorporate adapted materials and build any new content, publish to Moodle | 02/12/08 | 08/12/08 |  |  | IG |
| - Set up moodle environment | 09/12/08 | 09/12/08 |  |  | GB |
| - Full editorial QA of online materials, | 10/12/08 | 16/12/08 |  |  | GB |
| - Materials updated | 22/12/08 | 22/12/08 | Courses built | 8 | IG |
| #### WORKPACKAGE 8: Review and publication Objective: Course ready for study | 23/12/08 | 26/01/09 |  |  |  |
| - Final online QA by SME and AD, | 23/12/08 | 08/01/09 |  |  | SB. DG |
| - Update materials accordingly | 09/01/09 | 13/01/09 |  |  | IG |
| - Final sign-off | 19/01/09 | 19/01/09 |  |  | GB DG SB |
| - Publish materials. | 26/01/09 | 26/01/09 | Course ready for study | 9 | IG |
| #### WORKPACKAGE 9: Delivery Objective: Course delivered | 06/10/08 | 17/04/09 |  |  |  |
| - Advertise course, recruit students, identify course tutor | 06/10/08 | 27/01/09 |  |  | CK |
| - set up student profiles on Moodle, send login details to students | 26/01/09 | 28/01/09 |  |  | MT |
| - Run course (Tutoring, IT and admin support) | 28/01/09 | 08/04/09 |  |  | SB, CK, MT |
| - Archive course on completion | 17/04/09 | 17/04/09 | Course delivered | 10 | MT |
| #### WORKPACKAGE 10: Evaluation and dissemination Objective: Project Evaluated | 13/02/08 | 31/01/09 |  |  |  |
| - Participate in JISC peer review process | 20/02/08 | 31/01/09 |  |  | MM |
| - Review development process through reflective project blog and update plans accordingly | 13/02/08 | 31/01/09 |  |  | MM |
| - Evaluate course at each stage through standard sign off methodology (see above) | 28/02/08 | 31/01/09 |  |  | MM, GB |
| - Evaluate course delivery through reflective project blog and standard student evaluation forms. | 13/02/08 | 31/01/09 | Evaluation report | 11 | MM, CK, SB, GB |
| - Participate in Dissemination activities | 20/02/08 | 31/01/09 |  |  | MM |
| - Feed into any external JISC evaluation processes. | 20/02/08 | 31/01/09 |  |  | MM |
| #### WORKPACKAGE 11: Documentation and report writing Objective: All project documentation completed | 13/02/08 | 31/01/09 |  |  |  |
| - Write reports as required by JISC | 20/02/08 | 31/01/09 | Reporting completed | 12 | MM |
| - Deposit all project outputs in relevant repositories | 05/01/09 | 31/01/09 | Outputs deposited | 13 | MM, GB, DB |
| - Update existing project support documentation both print and online to reflect lessons learned. | 20/02/08 | 31/01/09 |  |  | MM, GB, SB |
| - Maintain project website and reflective blog. | 13/02/08 | 31/01/09 |  |  | Whole team |
| - Generate any additional documentation as required by project. | 05/01/09 | 31/01/09 | Documentation completed | 14 | MM, GB, SB |

Members of Project Team:							Other Abbreviations:

MM = Marion Manton		GB = Gerard Barker			LT = Learning technologist

TB = Thomas Box			SB = Sandie Byrne			AD = Academic Director

DG = David Grylls			DB = David Balch			SME = Subject matter expert

IG = Ian Gloster			MT = Mike Taylor

CK = Claire Kelly			NW = Nicola Warren